## Project roadmap
Quarter | Theme | Milestone | Owner | Status | Target
Q3 2026 | Sharing | Share links with PIN and expiry | Anna Kowalski | In progress | 2026-07-24
Q3 2026 | Sharing | Group sharing | Anna Kowalski | Planned | 2026-08-21
Q3 2026 | Search | Content search GA | Marco Rossi | In progress | 2026-09-11
Q3 2026 | Security | 2FA enforcement for admins | Elena Petrova | In progress | 2026-07-24
Q3 2026 | Security | API token expiry by default | Elena Petrova | Done | 2026-07-10
Q4 2026 | Platform | Desktop sync client beta | Tom Schmidt | Proposed | 2026-12-04
Q4 2026 | Storage | Tiered object storage | Marco Rossi | Planned | 2026-11-13
Q4 2026 | Company | Limassol office fully staffed | Tom Schmidt | Planned | 2026-12-18